Nice, this is the “how do I actually build and run this thing” part. I’ll give you all three pieces:

- Step-by-step implementation manual

- Diagram-based science explanation you can use at school

- Realistic budget and GFH replacement timeline (for one community unit)

I will assume one community unit serving a village, with about 1,000 L/h flow for a few hours per day.

## 1. Step-by-step implementation manual

### Phase 1: Define the pilot

- Clarify your goal

  - One pilot unit in a severely arsenic-affected village

  - Treat groundwater from a borewell to make it safe to drink

  - Show safe handling of arsenic-bearing waste (sludge + exhausted GFH)

  - Involve local school students in operation and basic monitoring

- Choose the site

  - Work with a district official / NGO to pick the village

  - Basic criteria:

    - Arsenic in handpumps above 50 µg/L

    - Iron clearly present (colour, metallic taste or test)

    - Poor or unreliable electricity

    - Willing panchayat and school

### Phase 2: Water testing and design

- Test the water from at least 2–3 local wells
Minimum parameters:

  - Arsenic

  - Iron

  - pH

  - Turbidity

  - (If possible) phosphate and silica

- Decide the design basis
Example design:

  - Raw water: arsenic ~ 100 µg/L, iron high

  - Flow: 1,000 L/h

  - Operation: 4 hours per day

  - Total treated water: about 4,000 L/day
Treatment train:

  - Borewell pump to elevated raw water tank

  - Iron removal filter

  - Activated carbon filter

  - GFH arsenic removal filter

  - Backwash filter and sludge barrel

  - Treated water tank and tap

### Phase 3: Sizing and procurement

- Size the main components (typical values)

  - Raw water tank: 2,000 L

  - Treated water tank: 1,000 L

  - Filters: 4 FRP vessels in series (iron, carbon, GFH, backwash)

  - GFH media: about 25–30 kg for one community unit

  - Pump: sized to deliver ~1,000 L/h to the raw water tank

  - Solar panel set large enough to run the pump in daylight hours

- Source equipment and media

  - FRP filters and tanks from a local water-treatment vendor

  - GFH from a reputable media supplier

  - Pipes, valves, stands, basic civil works done locally

  - Solar package from a local solar integrator

### Phase 4: Installation

- Civil and structural work

  - Concrete slab for filters and sludge barrel

  - Small platform or frame for tanks and solar structure

  - Secure fencing if needed

- Mechanical installation

  - Install borewell pump and connect to raw water tank

  - Install four filters in sequence: iron → carbon → GFH → backwash

  - Connect pipes:

    - Raw tank to iron filter

    - Iron filter to carbon filter

    - Carbon filter to GFH filter

    - GFH filter to backwash filter

    - Backwash filter to treated water tank

  - Install separate pipe from backwash filter outlet to sludge barrel

  - Install outlet tap from treated water tank

- Electrical and solar

  - Wire solar panels to controller and battery (if used)

  - Connect controller to borewell pump

  - Add simple switch and basic protection (fuse, MCB)

### Phase 5: Commissioning

- Media loading and rinsing

  - Fill iron filter with iron removal media, rinse to waste

  - Fill carbon filter with activated carbon, rinse until black fines are gone

  - Fill GFH filter with 25–30 kg GFH, rinse to waste as per supplier instructions

  - Fill backwash filter with appropriate media (sand or multi-grade), rinse

- Initial test run

  - Pump water to raw tank

  - Open flow through filters to treated tank

  - Monitor flow rate and check for leaks

  - After the system stabilises, test:

    - Arsenic at inlet and treated water

    - Iron, pH, turbidity at the outlet

- Community handover

  - Explain the flow path and safety aspects

  - Train 2–3 people (and students) on:

    - Starting and stopping the pump

    - Backwashing the filters as recommended

    - Keeping the sludge barrel closed

    - Not tampering with the GFH vessel

### Phase 6: Operation, maintenance and disposal

- Routine operation

  - Operate daily for the planned hours

  - Keep a simple log: date, hours run, basic observations

  - Backwash iron, carbon and backwash filters at regular intervals

  - Ensure all backwash water goes to the sludge barrel

- Monitoring

  - Test arsenic and iron in treated water periodically (for example, once a month using field kits, plus occasional lab confirmation)

  - Record any drop in performance

- Sludge barrel management

  - Allow solids to settle in the barrel

  - Occasionally decant clearer water from the top back to the raw water tank

  - Let sludge thicken at the bottom

  - When the barrel is nearly full, seal it and store in a safe, dry area for later transport

- GFH replacement and disposal

  - Based on flow and arsenic level, plan to replace GFH once per year (details in budget section below)

  - When media is exhausted:

    - Drain the GFH vessel

    - Scoop out the media into a sealed, labelled drum or double-bagged container

    - Load new GFH into the vessel and rinse according to instructions

    - Keep the sealed GFH waste in a safe place until it can be transported to a hazardous waste facility or central disposal point

## 2. Diagram-based science explanation (for school)

You can show this as three simple diagrams on a poster or slide.

### Diagram 1: Overall system

Groundwater (Borewell)

│

▼

Raw Water Tank (2000 L)

│

▼

Iron Removal Filter

│

▼

Activated Carbon Filter

│

▼

GFH Arsenic Removal Filter

│

▼

Backwash / Polishing Filter

│

▼

Treated Water Tank (1000 L)

│

▼

Community Tap

Solar panel powers the borewell pump that fills the raw water tank.

### Diagram 2: What happens in each filter

1. Iron Removal Filter

- Oxidises dissolved iron (Fe2+) to rust (Fe(OH)3)

- Rust particles get trapped in the filter

2. Activated Carbon Filter

- Adsorbs organic chemicals

- Improves taste and odour

3. GFH Arsenic Filter

- GFH grains have iron hydroxide surfaces

- Arsenate (As(V)) sticks to GFH surfaces

- Arsenic stays in the media, not in the water

4. Backwash / Polishing Filter

- Removes fine particles and remaining turbidity

- Also used to flush out trapped solids during backwash

### Diagram 3: Sludge and GFH waste management

Backwash water (high in iron, some arsenic)

│

▼

Arsenic Sludge Barrel

- Solids settle at bottom

- Clearer water on top

Top water:

- Carefully poured back to raw tank

Bottom sludge:

- Left to thicken

- Barrel sealed when nearly full

- Stored safely and later sent for proper disposal

Exhausted GFH:

- Removed from arsenic filter once per year

- Placed in a sealed, labelled drum

- Stored safely and sent to hazardous waste facility or

central disposal point

For a school audience, you can frame it as:

- “Where does the arsenic go?”
Into the GFH media and into sludge, not into the drinking water.

- “How do we make sure it never comes back?”
By sealing and safely disposing of the used media and sludge.

## 3. Realistic budget and GFH replacement timeline

This is a rough but reasonable budget for one community unit similar to your schematic, in Indian rupees (INR).

### A. Capital costs (one-time)

Approximate ranges for a system around 1,000 L/h, 4 hours per day:

| Item | Approximate Cost (INR) |
| --- | --- |
| Borewell drilling and pump | 50,000 – 70,000 |
| Solar panels, controller, wiring, small battery | 1,00,000 – 1,40,000 |
| Raw water tank (2000 L) + treated water tank (1000 L) | 25,000 – 35,000 |
| Four FRP filters (iron, carbon, GFH housing, backwash) | 90,000 – 1,20,000 |
| GFH media initial charge (~25–30 kg) | 15,000 – 20,000 |
| Iron removal and carbon media | 15,000 – 20,000 |
| Piping, valves, fittings, supports | 30,000 – 40,000 |
| Sludge barrel(s), concrete slab, minor civil works | 40,000 – 60,000 |
| Labour, installation, local transport | 30,000 – 50,000 |

Total typical range
About 4,00,000 to 5,00,000 INR for a complete solar powered community system, if you include all structural and civil work.

For a non-solar version (grid electricity), the cost could drop by around 1,00,000 to 1,40,000 INR.

### B. GFH replacement timeline (example calculation)

Assumptions:

- Flow: 1,000 L/h

- Operation: 4 hours per day

- Water treated: 4,000 L/day

- Arsenic in raw water: 100 µg/L (0.0001 g/L)

- Target: reduce to below 10 µg/L

- As a rough figure, assume effective GFH capacity around 5 g As per kg media (this is conservative and depends on water chemistry).

- Arsenic mass removed per day

  - 4,000 L/day × 0.0001 g/L = 0.4 g As removed per day

- Arsenic capacity of 1 kg GFH

  - 5 g As per kg media

- How long 1 kg of GFH lasts

  - 5 g / 0.4 g per day ≈ 12.5 days

So you need enough GFH for about one year of operation.

- GFH mass needed for one year

  - One year As load: 0.4 g/day × 365 ≈ 146 g As per year

  - At 5 g As per kg GFH:
146 g / 5 g per kg ≈ 29 kg GFH

So a 25–30 kg GFH bed is reasonable for about one year under those assumptions.

In practice, you would:

- Start with 25–30 kg GFH

- Monitor treated water arsenic monthly

- Replace the media when arsenic in the treated water begins to rise toward the limit (or at 12 months if all looks good)

### C. Annual operating costs (rough)

| Item | Approximate Cost per Year (INR) |
| --- | --- |
| GFH media replacement (25–30 kg) | 15,000 – 20,000 |
| Replacement carbon media | 4,000 – 6,000 |
| Occasional iron media top-up | 3,000 – 5,000 |
| Basic maintenance, plumber, small parts | 8,000 – 12,000 |
| Water testing and lab analysis | 5,000 – 10,000 |

Rough annual operating cost
About 35,000 – 50,000 INR per year for one unit.

If you tell me the exact flow and daily operating hours you want to design for (for example 500 L/h for 3 hours or 2,000 L/h for 4 hours), I can redo the GFH sizing and replacement timeline to match your exact pilot.